## Sheet1
Task | Primary | Secondary | Reassigned? | To Whom? | Complete | Due Date | Date Done
Exchange Contact Information | All |  |  |  | X | 2015-03-17 | 2015-03-13
Name Group/Notify Instructor | All | Donna |  |  | X | 2015-03-17 | 2015-03-13
Goal Statement | All | Donna |  |  |  | 2015-03-17 | 2015-03-13
Initial set of Business Rules | Maude | Conan |  |  |  | 2015-03-17
Assign each task | Donna | All |  |  |  | 2015-03-17 | 2015-03-13
Rough Schedule | Donna | All |  |  |  | 2015-03-17 | 2015-03-13
Rough Draft ERD | Conan | Maude |  |  |  | 2015-03-17
Review Rough Draft ERD | All |  |  |  |  | 2015-03-17
Data Dictionary | Conan | Object Designer |  |  |  | 2015-03-17
Planning Documents | Donna |  |  |  |  | 2015-04-21
Business Rules | Maude & Kyle | All |  |  |  | 2015-03-24
Entity-relationship Diagrams | Conan | Maude |  |  |  | 2015-03-24
Design of normalized tables | Calvin |  |  |  |  | 2015-03-31
Population of tables with actual data | Maude | Kyle & Conan |  |  |  | 2015-03-31
Five Queries | Calvin | Maude |  |  |  | 2015-04-07
Forms | Kyle | Maude |  |  |  | 2015-04-07
Five Reports | Calvin | Maude |  |  |  | 2015-04-14
Task | Primary | Secondary | Reassigned? | To Whom? | Complete | Due Date | Date Done
Integrated User Interface | Kyle |  |  |  |  | 2015-04-14
Package of Documentation | Donna |  |  |  |  | 2015-04-21
Oral Presentation | All |  |  |  |  | 2015-04-23
Simple user's manual/help file | Conan | Donna |  |  |  | 2015-04-21